## Baseline v2
Man Day in Hours | 9
Boomi Service Level Estimation Baseline (Development+Unit Testing)
Complexity |  | Efforts in Hours | Justification
Complex Services | Complex | 63 | Process or workflow service that orchestrate by multiple service invocations
Medium Complex | Medium Complex | 54 | Service with data aggregation, validation and transformation, Audit
Medium Services | Medium | 45 | Service with data aggregation, validation and transformation
Simple Medium | Simple Medium | 36 | Data Insert/Update/Query/Proxy Services
Simple Services | Simple | 27 | Simple routing and proxy
Enterprise Integration
Effort Distribution Baseline
Phase | Baseline Vals
Requirements | 10
Design | 15
Construction | 45
Unit Test and Test Execution | 20
PM and Delivery | 10
TOTAL | 100
Note: The above estimation baseline is applicable to projects that using ESB and SOA based tools only. *** Please recheck the values based on the specific tools and technologies since the complexity level may vary depending on the features of the product.

## Complexity Breaddown
Efforts in Hours | Complexity | Justification | No. of interfaces | Requirement (man hours) | Design (man hours) | Construction (man hours) | Test cases and execution (man hours) | PM and Delivery (man hours) | Total (man hours)
63 | Complex | Process or workflow service that orchestrate by multiple service invocations [OR] one to 7 or more mapping | 14 | 196 | 294 | 882 | 392 | 196 | 1960
54 | Medium Complex | Service with data aggregation, validation and transformation, Audit [OR] one to five or six mapping | 2 | 24 | 36 | 108 | 48 | 24 | 240
45 | Medium | Service with data aggregation, validation and transformation [OR] one to three or four mapping | 4 | 40 | 60 | 180 | 80 | 40 | 400
36 | Simple Medium | Data Insert/Update/Query/Proxy Services [OR] one to two mapping | 19 | 152 | 228 | 684 | 304 | 152 | 1520
27 | Simple | Simple routing and proxy [OR] one to one mapping | 20 | 144 | 216 | 648 | 288 | 144 | 1440
Total |  |  | 59 | 556 | 834 | 2502 | 1112 | 556 | 6280

## Interface Details
Sl. No. | Interface Name | Source | Target | Integration Type | Request / Response | Interface Source Type | Interface Target Type | Complexity | Requirements (man hours) | Design (man hours) | Construction (man hours) | Test case & Test Execution (man hours) | PM and Delivery (man hours) | Individual Total (man hours)
1 | Items | Merchandising | eCommerce | Batch | Y |  |  | Simple | 6 | 9 | 27 | 12 | 6 | 60
2 | Pricing | Merchandising | eCommerce | Batch / On-demand | Y |  |  | Simple | 6 | 9 | 27 | 12 | 6 | 60
3 | Suppliers | Financials | Merchandising | Real time | Y |  |  | Simple | 6 | 9 | 27 | 12 | 6 | 60
4 | GL Entries | Merchandising | Financials | Batch | N |  |  | Simple | 6 | 9 | 27 | 12 | 6 | 60
5 | Invoices | Merchandising | Financials | Batch | N |  |  | Simple | 6 | 9 | 27 | 12 | 6 | 60
6 | Customer Orders & Inventory Sync | eCommerce | WMS / OMS | Real time / On-demand | Y |  |  | Complex | 14 | 21 | 63 | 28 | 14 | 140
7 | DC To DC Transfers | WMS | WMS | Batch | Y |  |  | Simple | 6 | 9 | 27 | 12 | 6 | 60
8 | Item | Merchandising | WMS / OMS | Real time | N |  |  | Simple Medium | 8 | 12 | 36 | 16 | 8 | 80
9 | Item Supplier | Merchandising | WMS / OMS | Real time | N |  |  | Simple Medium | 8 | 12 | 36 | 16 | 8 | 80
10 | Item Image | Merchandising | WMS / OMS | Real time | N |  |  | Simple Medium | 8 | 12 | 36 | 16 | 8 | 80
11 | Item UPC | Merchandising | WMS / OMS | Batch | N |  |  | Simple Medium | 8 | 12 | 36 | 16 | 8 | 80
12 | Item BOM | Merchandising | WMS / OMS | Batch | N |  |  | Simple Medium | 8 | 12 | 36 | 16 | 8 | 80
13 | Store SOH | Merchandising | WMS / OMS | Real time | Y |  |  | Complex | 14 | 21 | 63 | 28 | 14 | 140
14 | Store Location | Merchandising | WMS / OMS | Real time | N |  |  | Simple Medium | 8 | 12 | 36 | 16 | 8 | 80
15 | Purchase Order | Merchandising | WMS / OMS | Real time | N |  |  | Simple Medium | 8 | 12 | 36 | 16 | 8 | 80
16 | Cycle Count | WMS / OMS | Merchandising | Batch |  |  |  | Simple Medium | 8 | 12 | 36 | 16 | 8 | 80
17 | Receipts (PO & Transfer) | WMS / OMS | Merchandising | Real time | Y |  |  | Simple Medium | 8 | 12 | 36 | 16 | 8 | 80
18 | PO ASN | WMS / OMS | Merchandising | Real time | Y |  |  | Simple Medium | 8 | 12 | 36 | 16 | 8 | 80
19 | Inventory Adjustments | WMS / OMS | Merchandising | Real time | Y |  |  | Simple Medium | 8 | 12 | 36 | 16 | 8 | 80
20 | Return To Vendor | WMS / OMS | Merchandising | Real time | Y |  |  | Simple Medium | 8 | 12 | 36 | 16 | 8 | 80
21 | Transfer Shipment ASN Out | WMS / OMS | Merchandising | Real time | Y |  |  | Simple Medium | 8 | 12 | 36 | 16 | 8 | 80
22 | SOH | Merchandising | Allocation | Batch | N |  |  | Simple | 6 | 9 | 27 | 12 | 6 | 60
23 | Allocation | Allocation | WMS / OMS | Real time | N |  |  | Simple Medium | 8 | 12 | 36 | 16 | 8 | 80
24 | ASN | WMS / OMS | Allocation | Real time | Y |  |  | Simple Medium | 8 | 12 | 36 | 16 | 8 | 80
25 | Sales Data Feed | WMS / OMS | CRM | Batch | N |  |  | Simple Medium | 8 | 12 | 36 | 16 | 8 | 80
26 | Foundation Data & Pricing | Merchandising | POS | Batch | N |  |  | Simple | 6 | 9 | 27 | 12 | 6 | 60
27 | SalesPosting | POS | Sales Audit | Batch | N |  |  | Simple | 6 | 9 | 27 | 12 | 6 | 60
28 | Retail Sales | Financials | Real Estate | Batch | N |  |  | Simple | 6 | 9 | 27 | 12 | 6 | 60
29 | Invoice | Real Estate | Financials | Batch | N |  |  | Simple | 6 | 9 | 27 | 12 | 6 | 60
30 | Payment | Financials | Real Estate | Batch | N |  |  | Simple | 6 | 9 | 27 | 12 | 6 | 60
31 | Payroll | Payroll | Financials | Batch |  |  |  | Simple | 6 | 9 | 27 | 12 | 6 | 60
32 | AP Invoice Payments | Financials | Payment provider | Batch |  |  |  | Simple | 6 | 9 | 27 | 12 | 6 | 60
33 | Employee Data | Financials | HRM | Batch |  |  |  | Simple | 6 | 9 | 27 | 12 | 6 | 60
34 | Customer operations | POS / eCommerce / Customer Service | CRM | Real time |  |  |  | Complex | 14 | 21 | 63 | 28 | 14 | 140
35 | Loyalty Points Sign-up | POS / eCommerce / mCommerce | Loyalty System | Real time |  |  |  | Complex | 14 | 21 | 63 | 28 | 14 | 140
36 | Gift card activation | POS / eCommerce / mCommerce | Gift card system | Real time |  |  |  | Complex | 14 | 21 | 63 | 28 | 14 | 140
37 | Tax calculation | POS / eCommerce / mCommerce / OMS / WMS | Tax System | Batch |  |  |  | Medium Complex | 12 | 18 | 54 | 24 | 12 | 120
38 | Fraud Check | eCommerce / mCommerce / OMS | Fraud Check System | Real time / On-demand |  |  |  | Medium | 10 | 15 | 45 | 20 | 10 | 100
39 | Address verification | POS / eCommerce / mCommerce | Address verification system | Real time |  |  |  | Medium | 10 | 15 | 45 | 20 | 10 | 100
40 | Payment | POS / eCommerce / mCommerce / OMS | Payment provider | Real time |  |  |  | Medium | 10 | 15 | 45 | 20 | 10 | 100
41 | 3rd party order taking sites | POS / eCommerce / mCommerce | Delivery aggregator | Real time |  |  |  | Medium | 10 | 15 | 45 | 20 | 10 | 100
42 | Order view | POS / eCommerce / mCommerce / Customer Service | OMS | Real time |  |  |  | Medium Complex | 12 | 18 | 54 | 24 | 12 | 120
43 | Returns / Exchange | POS / eCommerce / mCommerce / Customer Service / WMS | OMS | Real time |  |  |  | Complex | 14 | 21 | 63 | 28 | 14 | 140
44 | Analytics | POS / eCommerce / mCommerce / Merchandising / Allocation / CRM / 3rd party order taking sites / Financials | Analytics | Batch |  |  |  | Complex | 14 | 21 | 63 | 28 | 14 | 140
45 | Analytics | Analytics | Reporting | Batch |  |  |  | Simple | 6 | 9 | 27 | 12 | 6 | 60
46 | Store Inventory | POS | Inventory management system | Real time |  |  |  | Simple | 6 | 9 | 27 | 12 | 6 | 60
47 | Transportation and Logistics | WMS | Supplier | Batch |  |  |  | Simple | 6 | 9 | 27 | 12 | 6 | 60
48 | Transportation and Logistics | WMS | 3PL | Batch |  |  |  | Simple | 6 | 9 | 27 | 12 | 6 | 60
49 | Shipping Updates | OMS | WMS | Real time |  |  |  | Simple | 6 | 9 | 27 | 12 | 6 | 60
50 | Content management | eCommerce / mCommerce | CMS | Real time / On-demand / Batch |  |  |  | Simple Medium | 8 | 12 | 36 | 16 | 8 | 80
51 | Customer Experience | eCommerce / mCommerce | CX | Real time / On-demand / Batch |  |  |  | Simple Medium | 8 | 12 | 36 | 16 | 8 | 80
52 | Marketing | eCommerce / mCommerce | Marketing | Real time / On-demand / Batch |  |  |  | Simple Medium | 8 | 12 | 36 | 16 | 8 | 80
53 | Data Security | [6 empty] | Complex | 14 | 21 | 63 | 28 | 14 | 140
54 | API Security | [6 empty] | Complex | 14 | 21 | 63 | 28 | 14 | 140
55 | Notification | [6 empty] | Complex | 14 | 21 | 63 | 28 | 14 | 140
56 | Error/Exception Handling | [6 empty] | Complex | 14 | 21 | 63 | 28 | 14 | 140
57 | Data consolidation | [6 empty] | Complex | 14 | 21 | 63 | 28 | 14 | 140
58 | Data Quality / Transformation | [6 empty] | Complex | 14 | 21 | 63 | 28 | 14 | 140
59 | Logging | [6 empty] | Complex | 14 | 21 | 63 | 28 | 14 | 140
[9 empty] | 532 | 798 | 2394 | 1064 | 532 | 5320 | 33.25

## Effort&CostEstimates for Impl.
|  |  | Resource | Rate (USD/hr)
|  |  | Integration Tech Lead | 38
|  |  | Senior Integration Engineer | 35
Environment and Dependency Setup |  |  | Integration Engineer | 32
Environment Name | Effort (hrs) |  | Project Manager | 40
DEV | 40 |  | Integration Tester | 30
UAT | 40
PRODUCTION | 40 |  | Phases | Cost
CI/CD Setup (DEV, UAT and PROD) | 180 |  | Requirements | 20216
Total Environment and Dependency | 300 | A | Design | 30324
|  |  | Dev | 76608
Interface Development and Support |  |  | Testing | 31920
All Interface Total Efforts | 5320 |  | UAT, Go-Live | 17024
UAT and Prod Bug Fixes and HyperCare | 532 |  | Setup | 11400
Total Interface Development and Support | 5852 | B | Auras Cost | 0
187492
|  |  | PM/Delivery effort | 21280
Consolidated Project Hours |  |  | Total | 208772
Total Environment and Dependency | 300 | A | Contingency (10%) | 20877.2
Total Interface Development and Support | 5852 | B | Total Cost | 229649.2
Contigency Hours | 615.2 | Others
Total Consolidated Project Hours | 6467.2 | A+B+Others
Note on C10: Can be made to zero if Auras is not used.

## Assessment and POC Estimate
Role | Rate (USD/Hr)
Enterprise Integration Architect | 105
Lead Enterprise Integration SME | 35
Senior Integration Engineer | 35
Integration Engineer | 30
Assessment Phase |  |  |  | 6 |  | 4
Resource | Rate | Utilization | Working hours | Effort for 2 weeks | Cost for 2 weeks | Effort for 4 weeks (Hours) | Cost for 4 weeks
| (USD/HR) | % | per week | (Hours) | (USD) |  | (USD)
Enterprise Integration Architect | 115 | 100 | 40 | 240 | 27600 | 160 | 18400
BA Retail | 95 | 100 | 40 | 160 | 15200 | 160 | 15200
Lead Enterprise Integration SME | 33 | 100 | 45 | 270 | 8910 | 180 | 5940
[5 empty] | 51710 |  | 39540
Total cost Range
$12,350 ß à $24,700
(Approx. Cost range for 2 - 4 weeks of Assessment)
POC Phase |  |  |  | 6
Resource | Rate | Utilization | Working hours | Effort for <above> weeks | Cost for <above> weeks
| (USD/HR) | % | per week | (Hours) | (USD)
Enterprise Integration Architect | 115 | 50 | 40 | 120 | 13800
Lead Enterprise Integration SME | 33 | 100 | 45 | 270 | 8910
BA Retail | 95 | 100 | 40 | 240 | 22800
Senior Integration Engineer | 30 | 67 | 45 | 180.9 | 5427
50937
Total cost Range
[6 empty] | 3 Weeks | 13269 | (If EIA is billed 115 USD/hour with a 40 hrs working week and 40% of utilization) (If LEIS is billed 35 USD/hour with a 45 hrs working week and 100% of utilization) (If SIE is billed 32 USD/hour with a 45 hrs working week and 70% of utilization)
[6 empty] | 6 Weeks | 26538
[6 empty] | 8 Weeks | 35384

## Resource Plan and Estimate
Role | Rate (USD/Hr) |  |  |  |  | Legend | Discovery
Enterprise Integration Architect | 115 | [5 empty] | Analysis
Lead Enterprise Integration SME | 35 | [5 empty] | Design
Senior Integration Engineer | 32 | [5 empty] | Development
Integration Engineer | 30 | [5 empty] | Test
Integration Tester | 30 | [5 empty] | UAT
Technical Manager | 40 | [5 empty] | GoLive
PM Effort
Phase 3 Integrations
Hours
Resource Deployment |  | Discovery |  |  |  |  | Analysis |  |  |  |  | Design and Development |  |  |  |  | Design and Development |  |  |  |  | Development and Testing | [8 empty] | UAT & Go-Live
Resources | Onsite /Offsite | Month 1 |  |  |  |  | Month 2 |  |  |  |  | Month 3 |  |  |  |  | Month 4 |  |  |  |  | Month 5 |  |  |  | Month 6 |  |  |  |  | Month 7
|  | W1 | W2 | W3 | W4 |  | W5 | W6 | W7 | W8 |  | W9 | W10 | W11 | W12 |  | W13 | W14 | W15 | W16 |  | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 |  | W25 | W26 | W27 | W28
Technical Manager | 0 |  |  |  |  | 0 | 40 | 40 | 40 | 40 | 160 | 20 | 20 | 20 | 20 | 80 | 10 | 10 | 10 | 10 | 40 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 80 | 5 | 5 | 15 | 15 | 40
Enterprise Integration Architect | 0 | 40 | 40 | 40 | 40 | 160 | 40 |  |  |  | 40 |  |  |  |  | 0 |  |  |  |  | 0 | [8 empty] | 0 |  |  |  |  | 0
Lead Enterprise Integration SME | 0 | 45 | 45 | 45 | 45 | 180 | 45 | 45 | 45 | 45 | 180 | 45 | 45 | 45 | 45 | 180 | 45 | 45 | 45 | 45 | 180 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 360 | 45 | 45 | 45 | 45 | 180
Senior Integration Engineer | 0 |  |  |  |  | 0 | 90 | 90 | 90 | 90 | 360 | 90 | 90 | 90 | 90 | 360 | 90 | 90 | 90 | 90 | 360 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 720 | 45 | 45 | 45 | 45 | 180
Integration Engineer | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 135 | 135 | 270 | 135 | 135 | 135 | 135 | 540 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 1080 | 45 | 45 | 45 | 45 | 180
Integration Tester | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 45 | 45 | 45 | 135 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 720 | 90 | 45 | 45 |  | 180
|  | 85 | 85 | 85 | 85 |  | 215 | 175 | 175 | 175 | [11 empty] | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 |  | 230 | 185 | 195 | 150
|  | Discovery | Analysis | Design & Dev | Design & Dev | Dev & Test | UAT & Go-Live
Resource | Rate (USD/hr) | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 - 6 | Month 7
Technical Manager | 40 | 0 | 6400 | 3200 | 1600 | 3200 | 1600
Enterprise Integration Architect | 115 | 18400 | 4600 | 0 | 0 | 0 | 0
Lead Enterprise Integration SME | 35 | 6300 | 6300 | 6300 | 6300 | 12600 | 6300
Senior Integration Engineer | 32 | 0 | 11520 | 11520 | 11520 | 23040 | 5760
Integration Engineer | 30 | 0 | 0 | 8100 | 16200 | 32400 | 5400
Integration Tester | 30 | 0 | 0 | 0 | 4050 | 21600 | 5400 |  |  |  | 10% Contingency
|  | 24700 | 28820 | 29120 | 39670 | 92840 | 24460 | 239610 |  |  | 263571
Role | Rate (USD/Hr)
Enterprise Integration Architect | 115
Lead Enterprise Integration SME | 38
Senior Integration Engineer | 35
Integration Engineer | 30 |  |  | 30
Integration Tester | 30
Technical Manager | 40
|  | 2 months |  | 2 months |  | 2 months |  | 2 months |  | 2 months
| Hr Per Wave | Wave 0 | Rate | Wave 1 | Rate | Wave 2 | Rate | Wave 3 | Rate | Wave 4 | Rate
Interfaces |  | 8 |  | 12 |  | 12 |  | 12 |  | 12
Architect | 80
Platform Setup and others |  | 80 | 9200 | 80 | 9200 | 80 | 9200 | 80 | 9200 | 80 | 9200
Lead Integraion Engineer | 320
Interface Impl(2 nos) |  | 320 | 12160 | 320 | 12160 | 320 | 12160 | 320 | 12160 | 320 | 12160
Integration Engineer | 320
Interface Impl(2 nos) |  | 500 | 15000 | 320 | 9600 | 320 | 9600 | 320 | 9600 | 320 | 9600
Integration Engineer | 320
Interface Impl(2 nos) |  | 320 | 9600 | 320 | 9600 | 320 | 9600 | 320 | 9600 | 320 | 9600
Integration Tester | 160
Interface Impl(2 nos) |  | 320 | 9600 | 320 | 9600 | 320 | 9600 | 320 | 9600 | 320 | 9600
Project Manager | 80
Management |  | 80 | 3200 | 80 | 3200 | 80 | 3200 | 80 | 3200 | 80 | 3200
|  |  | 58760 |  | 53360 |  | 53360 |  | 53360 |  | 53360

## Timeline
EI Assessment Phases | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
Analyze
(systems, infrastructure, APIs, End Points)
Strategize
(with Objectives and Priorities)
Define
(Roadmap, End State Architecture)
Plan
(Approach, Timeline, Effort, Artefacts)
EI Development Phase | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10
Wave-0 | Month 1: Build, test, deploy
Wave-1 | Month 3: Build, test, deploy
Wave-2 | Month 5: Build, test, deploy
Wave-3 | Month 7: Build, test, deploy
Wave-4 | Month 9: Build, test, deploy
Role | Month 1: Rate (USD/Hr); Month 2: Effort (Hr); Month 3: Cost (USD)
Enterprise Integration Architect | Month 1: 115; Month 2: 400; Month 3: 46000
Lead Enterprise Integration SME | Month 1: 33; Month 2: 1600; Month 3: 52800
Integration Engineer | Month 1: 26; Month 2: 3380; Month 3: 87880
Retail BA | Month 1: 95; Month 2: 1600; Month 3: 152000
Senior Integration QA | Month 1: 32; Month 2: 1600; Month 3: 51200
Integration Tester | Month 1: 30; Month 2: 1600; Month 3: 48000
Technical Manager | Month 1: 40; Month 2: 400; Month 3: 16000
|  | Total | 453880

## R&R
Assessment
Phases | Activities | Casey's Mgmt | Casey's Project Manager | Casey's SME | Casey's Infra Team | Aspire Mgmt | Aspire Integration Architect | Aspire Lead Integration Engineer
Analyse | Understand Casey’s digital experience strategy | ✔ |  | ✔ | ✔ |  | ✔
| Understand Casey’s roadmap and integration needs | ✔ |  | ✔ |  |  | ✔
| Understand the existing set of Systems for Integrations |  | ✔ | ✔ | ✔ |  | ✔ | ✔
| Analyze the current implementation | [5 empty] | ✔ | ✔
Strategise | Align with Business Objectives and priorities | [5 empty] | ✔
| Process | [5 empty] | ✔ | ✔
| Applications | [5 empty] | ✔ | ✔
| Data | [5 empty] | ✔ | ✔
| Network Mappings | [5 empty] | ✔ | ✔
Plan | Transition Roadmap to future state | ✔ |  |  | ✔ |  | ✔
| Derive TCO for recommended platform | ✔ |  |  |  |  | ✔
| Effort Estimate | [5 empty] | ✔ | ✔
| Cost for implementing target solution | [5 empty] | ✔ | ✔
| Timeline for implementing target solution | [5 empty] | ✔ | ✔
Define | End State Architecture | [5 empty] | ✔
| Final Revisited estimate | [5 empty] | ✔ | ✔
| Pilot Program Scope planning and finalization | [5 empty] | ✔ | ✔
| Plan, Timeline, Effort and Cost to reach Target Solution | [5 empty] | ✔ | ✔
| Closure | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
PoC
Phases | Activities | Casey's Mgmt | Casey's Project Manager | Casey's SME | Casey's Infra Team | Aspire Mgmt | Aspire Tech Manager | Aspire Integration Architect | Aspire Integration Lead Engineer
Initiation | Budget and SOW Approval | ✔ | ✔ |  |  | ✔ | ✔
| Team Onboarding |  | ✔ |  | ✔ | ✔ | ✔
| Project Kickoff | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
| Environment Readiness |  | ✔ | ✔ | ✔ |  | ✔ | ✔
Analysis | Study Interfaces, Logics and Mapping |  | ✔ | ✔ |  |  | ✔ | ✔
| Review Data Mapping |  | ✔ |  |  |  | ✔ | ✔
| Review Workflow |  | ✔ |  |  |  | ✔ | ✔
| Review and capture NFRs |  | ✔ |  |  |  | ✔ | ✔
| Prepare Technical Specification | [5 empty] | ✔ | ✔
| Review Technical Specification |  |  | ✔ |  |  | ✔ | ✔
| Approve Spec, Plan and Phases |  | ✔ | ✔ |  |  | ✔ | ✔
Design and Development | Interface Consolidations |  |  | ✔ |  |  | ✔ | ✔
| Framework Models |  |  | ✔ |  |  |  | ✔
| Guidelines and Principles |  |  | ✔ |  |  |  | ✔
| Analysis & Detailed Design | [5 empty] | ✔ | ✔ | ✔
| LLD Finalization | [5 empty] | ✔ | ✔ | ✔
| Develop/Unit testing | [7 empty] | ✔
Integration Testing | Test Plan and case preparation
| Integration Testing | [6 empty] | ✔
Defect Logging / Tracking
| Defect Fixes | [7 empty] | ✔
| Environment setup (QA) |  |  |  | ✔ |  |  | ✔ | ✔
Pilot Acceptance | Pilot Deployment |  |  |  | ✔ |  |  | ✔ | ✔
| Pilot Evaluation | ✔ |  | ✔ | ✔ |  |  | ✔ | ✔
| Pilot Implementation Attributes |  |  | ✔ |  |  |  | ✔ | ✔
| Closure | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
Implementation
Phases | Activities | Casey's Mgmt | Casey's Project Manager | Casey's SME | Casey's Infra Team | Aspire Mgmt | Aspire Tech Manager | Aspire Integration Architect | Aspire Integration Engineers | Aspire Integration Testers
Initiation | Budget and SOW Approval | ✔ | ✔ |  |  | ✔ | ✔
| Team Onboarding |  | ✔ |  | ✔ | ✔ | ✔
| Project Kickoff | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
| Environment Readiness |  | ✔ | ✔ | ✔ |  | ✔ | ✔
Analysis | Study Interfaces, Logics and Mapping |  | ✔ | ✔ |  |  | ✔ | ✔
| Review Data Mapping |  | ✔ |  |  |  | ✔ | ✔
| Review Workflow |  | ✔ |  |  |  | ✔ | ✔
| Review and capture NFRs |  | ✔ |  |  |  | ✔ | ✔
| Prepare Technical Specification | [5 empty] | ✔ | ✔
| Review Technical Specification |  |  | ✔ |  |  | ✔ | ✔
| Approve Spec, Plan and Phases |  | ✔ | ✔ |  |  | ✔ | ✔
Design and Development | Interface Consolidations |  |  | ✔ |  |  | ✔ | ✔
| Framework Models |  |  | ✔ |  |  |  | ✔
| Guidelines and Principles |  |  | ✔ |  |  |  | ✔
| Analysis & Detailed Design | [5 empty] | ✔ | ✔ | ✔
| LLD Finalization | [5 empty] | ✔ | ✔ | ✔
| Develop/Unit testing | [7 empty] | ✔
Integration Testing | Test Plan and case preparation | [8 empty] | ✔
| Integration Testing | [6 empty] | ✔ |  | ✔
| Defect Logging / Tracking | [8 empty] | ✔
| Defect Fixes | [7 empty] | ✔
| Environment setup (QA) |  |  |  | ✔ |  |  | ✔ | ✔ | ✔
Release | Deployment UAT |  |  |  | ✔ |  |  | ✔
| User Acceptance - Succcess Criteria |  |  |  | ✔ |  |  | ✔ | ✔
| Customer - End Validation / External Invocation |  | ✔ | ✔ | ✔ |  |  | ✔
| Monitoring Performance |  | ✔ |  | ✔ |  | ✔ | ✔
| Knowledge Transfer | ✔ | ✔ |  | ✔ |  | ✔ | ✔ | ✔
| Closure | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔

## Assumptions
Assumption
1. Considering only two interfaces for the estimate. 2. Any extra integration points in the future will incur change in the estimates. 3. We are going to use Boomi Trading Partner feature for the integration. 4. The estimates are all based on very high level information and are subjeced to change during the discovery phase. i.e. If there are any new system that are involved other than JDE and CW1, the estimates make differ.
TBD